## Bug Summary Report
| Bug Summary Report |  |  |  | Team 2
Bugs |  | 20
Status |  |  |  | Priority
To Do | In Progress | Review | Done | Low | Medium | High
22 | 0 |  | 0 | 2 | 4 | 7
Bug Title |  |  |  |  | Priority | Status | Sprint | Feature | TestCases
HRM-Login Page-Login Credentials are not case-sensitive |  |  |  |  | High | To Do | SP_1 | 1- Login | 10 |  | 2
HRM-Login page-verify browser back button after login |  |  |  |  | High | To Do | SP_1 | 2- Logout | 2
HRM-PIM-The Employee ID Field is Allowing Manual Input of any Unique Number During Employee Addition |  |  |  |  | High | To Do | SP_1 | 3-PIM | 26 |  | 7
HRM-PIM- System Allows Creation of Multiple Employee Records with Identical Names. |  |  |  |  | High | To Do | SP_1 | 4-Info | 22 |  | 2
HRM-PIM-System Retained Employee Information Without an Employee ID. |  |  |  |  | High | To Do | SP_1 | 5-Admin-user management | 20 | 20 | 2 | 2
HRM-PIM-​System Allows Saving New Employee Record Without Required Middle Name. |  |  |  |  | Low | To Do | SP_1
HRM-PIM-Pagination status message is missing . |  |  |  |  | Medium | To Do | SP_1
HRM-PIM-Employee registration with Invalid Data Type. |  |  |  |  | High | To Do | SP_1
HRM-PIM_ Accepted invalid image dimension. |  |  |  |  | Low | To Do | SP_1
HRM- My Info- Date Of Birth Format |  |  |  |  | Medium | To Do | SP_1
HRM- My Info- Check Employee ID Field |  |  |  |  | Medium | To Do | SP_1
HRM-AdminPage-System allows disabling admin system user |  |  |  |  | High | To Do | SP_1
HRM-AdminPage -System Can't display user admin edited data in records found users list |  |  |  |  | Medium | To Do | SP_1